## 411762
Chamundeshwari Electricity Supply Corporation Limited
City Sub Division.
EST No.:- TSK - 417 DATE:-16.09.2022
Estimate prepared for replacement of existing detoriated poles for LT line of DTC- 411762,411773 at Rajkumarnagara , Adarshanagara in Uttarabadavane O&M section, City sub-divison, CESC, Hassan .
Part-A:-
Sl. No | Materials | Unit | Qty | Material |  | Labour
|  |  |  | Rate | Amount | Rate | Amount
1 | 8 mtrs RCC poles | Nos | 5 | 5306 | 26530 | 1072 | 5360
2 | LT 4 Pin Cross Arm with clamps, bolts, nuts & washers with brace - MS | Set | 5 | 439 | 2195 | 122 | 610
3 | LT 2 Pin Cross Arm with clamps, bolts, nuts & washers with brace - MS | Set | 5 | 274 | 1370 | 122 | 610
4 | 1.1 kV Ceramic Pin Insulator With GI pin | No | 10 | 65 | 650 | 0 | 0
5 | No .8 KN Strain Insulator | Nos | 10 | 25 | 250 | 0 | 0
6 | Rabbit ACSR Conductor +1.5% Sag + extra for joints & jumps | kms | 0.05 | 61515 | 3075.75 | 3299 | 164.95
7 | Supply of PVC insulated wire 10 Sq.mm | Mtr | 100 | 30.42 | 3042 | 0 | 0
8 | Miscellaneous material (Guy wire etc) and labour charges | L/s | --- | --- | 87 | --- | 55
9 | Total cost of Material & labour charges |  |  |  | 37199.75 |  | 6799.95
10 | Special Locality allowance 40% of labour charges | [5 empty] | 2719.98
11 | GST @18% | [5 empty] | 1713.5874
12 | ESI PF @ 18.36% | [5 empty] | 1747.8591
13 | Employees cost @ 20% on LC & LA | [5 empty] | 1903.986
14 | Transportation cost from stores to site (wherever applicable at 2 % on material cost) | [5 empty] | 743.995
15 | Contingencies @ 2% on metirial and labour | [5 empty] | 934.3936
16 | Sub Total |  |  |  | 37199.75 |  | 16563.7511
TOTAL ESTIMATE COST Rs. |  |  |  |  | 53763.5011
Part-B :-Decommission portion
Sl. No | Materials | Unit | Qty | Material |  | Labour
|  |  |  | Rate | Amount | Rate | Amount
1 | Releasing of 8 mtrs RCC poles | Nos | 5 | 0 | 0 | 1072 | 4824
2 | Releaseing and re-fixing of existing street light / OH service mains /Cables | Nos | 50 | 0 | 0 | 75 | 3750
3 | Releaseing of 4 pin x arms | Nos | 5 | 0 | 0 | 122 | 549
4 | Releasing & re-stringing of Rabbit ACSR conductor | Km | 0.9 | 0 | 0 | 3299 | 5641.29
5 | Miscellaneous material (Guy wire etc) and labour charges | L/s | --- | --- | 0 | --- | 36
6 | Total cost of Material & labour charges |  |  |  | 0 |  | 14800.29
7 | Special Locality allowance 40% of labour charges | [5 empty] | 5920.116
8 | GST @18% | [5 empty] | 3729.6731
9 | ESI PF @ 18.36% | [5 empty] | 3804.2665
10 | Employees cost @ 20% on LC & LA | [5 empty] | 4144.0812
11 | Transportation cost from stores to site (wherever applicable at 2 % on material cost) | [5 empty] | 0
12 | Contingencies @ 2% on metirial and labour | [5 empty] | 414.4081
13 | Sub Total |  |  |  | 0 |  | 32812.8349
TOTAL ESTIMATE COST Rs. |  |  |  |  | 32812.8349
Part -C :- Decommission portion Data to be furnished by field staff
Sl no | Particulars | Unit | Qty | Status | DOC | DOR
1 | Releasing of 8 Mtr RCC pole | Nos | 5 | Scrap | 1999 | After Work completion
2 | Releasing of 4 pin X-arm | Set | 5 | Scrap | 1999
Part -D :- Data to be furnished by Accounts staff
SL no | Particulars | Unit | Status | QTY | OV | DV | WDV
1 | Released 8 Mtr RCC pole skeleton | kgs | Scrap | 05*15= 75 kg
2 | Released 4 pin X-arm | kgs | Scrap | 5 * 2 = 10 kg
Asst Asst Account Officer Account Officer
O & M Division, CESC, Hassan O & M Division, CESC, Hassan O & M Division, CESC, Hassan
Chamundeshwari Electricity Supply Corporation Limited
Uttarabadavane Section, CSD, Hassan.
EST No.:- TSK - 417 DATE:-16.09.2022
Estimate prepared for replacement of existing detoriated poles for LT line of DTC- 411762,411773 at Rajkumarnagara , Adarshanagara in Uttarabadavane O&M section, City sub-divison, CESC, Hassan .
| Abstract: | Part A : |  | 53763.5011
|  | Part B : |  | 32812.8349
| GEI Charges : |  |  | 500
| Total cost of Estimate : |  |  | 87076.3361
Certificate:- I have prepared this estimate by using CESC Current SR for most safe and economical way of executing the work.
Report :-
This is an estimate cost of Rs,87076 /- is prepared for for replacement of existing detoriated poles for LT line of DTC- 411762,411773 at Rajkumarnagara , Adarshanagara in Uttarabadavane O&M section, City sub-divison, CESC, Hassan .
This estimate has been prepared for replacement of existing detoriated poles for LT line of DTC - 411762 - RAJ KUMAR NAGAR TC -100 kva , DTC - 411773 - ADARASH NAGAR TC- 100 kva , LT Line network poles are completely Detoriated & it is in hazardous condition, and it may damage to public life and also to our Distribution transformer ,hence this estimate is prepared for replacement of existing detoriated for LT line poles as shown in the sketch , all the required materials and labour are made provision in the estimate and existing materials using. As such it is requested to sanction the estimate as early as possible to carry out the work.
The proposed work is as follows :-
1. Replacement of existing detoriated 8 mtr RCC poles by proposed 8 mtr RCC poles as shown in the sketch.
2. Released pole skeleton , 4pin x arms as shown in the sketch , return to be Divisional store.
3 | Total cost of Estimate :- | 87076.3361
All necessary provisions are made in this estimate hence this estimate may kindly be sanctioned for execution the work.